## Sheet1
| Date | Goal | Version | Notifications out | Addenums
| 2022-09-01 | Meeting to end all meetings! | V1 -- Living Doc
| 2022-09-02 | Write up Fst Results | V1 -- Living Doc |  | GLM Fst --
| 2022-09-03 |  | V1 -- Living Doc
| 2022-09-04 |  | V1 -- Living Doc
1 | 2022-09-05 | Labor day | V1 -- Living Doc
2 | 2022-09-06 |  | V1 -- Living Doc
3 | 2022-09-07 | Narrative check | V1 -- Living Doc
4 | 2022-09-08 |  | V1 -- Living Doc
5 | 2022-09-09 | Address all standing "numerical" and "minor" comments | V1 -- Living Doc
6 | 2022-09-10 |  | V1 -- Living Doc
7 | 2022-09-11 |  | V1 -- Living Doc
1 | 2022-09-12 |  | V1 -- Living Doc
2 | 2022-09-13 |  | V1 -- Living Doc
3 | 2022-09-14 |  | V1 -- Living Doc
4 | 2022-09-15 |  | V1 -- Living Doc
5 | 2022-09-16 | Draft #2 is live (Main Figures Synchrozined) | V2 -- Finalized narrative | Alan notified
6 | 2022-09-17 |  | V2 -- Finalized narrative
7 | 2022-09-18 |  | V2 -- Finalized narrative
1 | 2022-09-19 |  | V2 -- Finalized narrative
2 | 2022-09-20 |  | V2 -- Finalized narrative
3 | 2022-09-21 |  | V2 -- Finalized narrative
4 | 2022-09-22 |  | V2 -- Finalized narrative | Slack chanel is notified
5 | 2022-09-23 | Supplementary tables and figures are fully synchronized to V2 | V2 -- Finalized narrative | Ready for co-author review
6 | 2022-09-24 |  | V2 -- Finalized narrative
7 | 2022-09-25 |  | V2 -- Finalized narrative
1 | 2022-09-26 | Internal Review Period | V2 -- Finalized narrative
2 | 2022-09-27 |  | V2 -- Finalized narrative
3 | 2022-09-28 |  | V2 -- Finalized narrative
4 | 2022-09-29 |  | V2 -- Finalized narrative
5 | 2022-09-30 | All SRA submitted; supplementary table 1 (SRA tables) made final | V2 -- Finalized narrative
6 | 2022-10-01 |  | V2 -- Finalized narrative
7 | 2022-10-02 |  | V2 -- Finalized narrative
1 | 2022-10-03 | Internal Review Period | V2 -- Finalized narrative
2 | 2022-10-04 |  | V2 -- Finalized narrative
3 | 2022-10-05 |  | V2 -- Finalized narrative
4 | 2022-10-06 |  | V2 -- Finalized narrative
5 | 2022-10-07 | Co-author reviews due | V3 -- The pre-print
6 | 2022-10-08 |  | V3 -- The pre-print
7 | 2022-10-09 |  | V3 -- The pre-print
1 | 2022-10-10 | Draft #3 -- "incorporate comments" | V3 -- The pre-print
2 | 2022-10-11 |  | V3 -- The pre-print
3 | 2022-10-12 |  | V3 -- The pre-print
4 | 2022-10-13 |  | V3 -- The pre-print
5 | 2022-10-14 | Paper in pre-print form (unless new analyses needed) | V3 -- The pre-print